## Sheet1
Pricing Report
Generated: 07/29/2024, 06:48 PM
RQST By: ARAMIS
**** CONSTRUCTION DETAILS ****
Part A
CFAS Project #: A02SMVJ
CMC: ALHMG
FRC: 845C
Pricing Date: 07/29/2024
| ITEM DESCRIPTION | MCF | FKF | QTY | UNIT COST | AMOUNT
| HANDHOLE10X15 | 0 | 0 | 7 | Exempt | 0
| HHOLE17X30X24 | 0 | 0 | 2 | Exempt | 0
| HHOLE-17X30X18 | 0 | 0 | 1 | Exempt | 0
| 10FT-GRD-ROD | 0 | 0 | 6 | Exempt | 0
| INNERDUCT-1 | 0 | 0 | 91 | Exempt | 0
| 5BQ2MT-144 | 0 | 14.4 | 110 | 0.79 | 86.9
| 5BQ2MR-432 | 0 | 69.984 | 172 | 2.01 | 345.72
| CONT-PL-CABLE | 0 | 0 | 385 | Exempt | 0
| FNAP-CBL-024EUC | 0 | 47.736 | 2019 | 0.36 | 726.84
| FNAP-CBL-048EUC | 0 | 83.28 | 1755 | 0.5 | 877.5
| EVOLV4/10OTIP | 0 | 0.04 | 10 | 107.39 | 1073.9
|  | ======= | ======= |  |  | =======
|  | 0 | 215.44 |  |  | 3110.86
| EXEMPT MATERIAL --- TELCO |  |  | 47.46 HRS | 35.5 | 1684.96
| SUPPLY EXPENSE |  |  | 4795.82 | 0.05 | 239.79
** | TOTAL MATERIAL |  |  |  |  | 5035.61
| PLACING LABOR |  |  | 7.73 HRS | 157.89 | 1220.27
| SPLICING LABOR |  |  | 39.73 HRS | 157.89 | 6272.9
** | TOTAL LABOR |  |  |  |  | 7493.17
| CONTRACT |  |  |  |  | 40210.83
| COST ADJUSTMENT - CONT |  |  |  |  | 20
** | TOTAL CONTRACT |  |  |  |  | 40230.83
| ENGINEERING |  |  | 29.03 HRS | 137.92 | 4004.04
** | TOTAL ENGINEERING |  |  |  |  | 4004.04
| TOTAL MATL, LABOR, CONTRACT, ENGR |  |  |  |  | 56763.66
| COST ADJUSTMENT - OTHER |  |  |  |  | 13443
** | GRAND TOTAL |  |  |  |  | 70206.66
| LABOR HOURS: |  |  | 47.46
| ENGR HOURS: |  |  | 29.03
| OVERHEAD COST: |  |  | 0
Generated: 07/29/2024, 06:48 PM
RQST By: ARAMIS
**** CONSTRUCTION DETAILS ****
Part A
CFAS Project #: A02SMVJ
CMC: ALHMG
FRC: 822C
Pricing Date: 07/29/2024
| ITEM DESCRIPTION | MCF | FKF | QTY | UNIT COST | AMOUNT
| TREE | 0 | 0 | 4499 | Exempt | 0
| EVOLV8/10OTIP | 0 | 0.152 | 19 | Exempt | 0
| EVOLV4/10OTIP | 0 | 0.388 | 97 | 107.39 | 10416.83
| STRAND-6 | 0 | 0 | 3006 | Exempt | 0
| FIBER-TELCO | 0 | 0 | 3149 | Exempt | 0
| 5BQ2MR-432 | 0 | 164.592 | 391 | 2.01 | 785.91
| FNAP-CBL-024 | 0 | 296.784 | 12506 | 0.32 | 4001.92
| FNAP-CBL-216EUC | 0 | 1358.424 | 6369 | 1.8 | 11464.2
| FNAP-CBL-144 | 0 | 1125.648 | 7897 | 0.98 | 7739.06
| 5B92MT-072 | 0 | 118.224 | 1662 | 0.39 | 648.18
| FNAP-CBL-048 | 0 | 449.424 | 9443 | 0.45 | 4249.35
| FNAP-CBL-072 | 0 | 338.256 | 4738 | 0.6 | 2842.8
| FNAP-CBL-432EUC | 0 | 3349.296 | 7813 | 2.67 | 20860.71
|  | ======= | ======= |  |  | =======
|  | 0 | 7201.188 |  |  | 63008.96
| EXEMPT MATERIAL --- TELCO |  |  | 1022.00 HRS | 35.5 | 36285.43
| SUPPLY EXPENSE |  |  | 99294.39 | 0.05 | 4964.72
** | TOTAL MATERIAL |  |  |  |  | 104259.11
| PLACING LABOR |  |  | 682.98 HRS | 157.89 | 107835.5
| SPLICING LABOR |  |  | 339.03 HRS | 157.89 | 53528.8
** | TOTAL LABOR |  |  |  |  | 161364.3
| CONTRACT |  |  |  |  | 11452.62
** | TOTAL CONTRACT |  |  |  |  | 11452.62
| ENGINEERING |  |  | 129.81 HRS | 137.92 | 17903.83
** | TOTAL ENGINEERING |  |  |  |  | 17903.83
| TOTAL MATL, LABOR, CONTRACT, ENGR |  |  |  |  | 294979.86
| COST ADJUSTMENT - OTHER |  |  |  |  | 79421
** | GRAND TOTAL |  |  |  |  | 374400.86
| LABOR HOURS: |  |  | 1022
| ENGR HOURS: |  |  | 129.81
| OVERHEAD COST: |  |  | 0
Generated: 07/29/2024, 06:48 PM
RQST By: ARAMIS
**** CONSTRUCTION DETAILS ****
Part A
CFAS Project #: A02SMVJ
CMC: ALHMG
FRC: 1C
Pricing Date: 07/29/2024
| ITEM DESCRIPTION | MCF | FKF | QTY | UNIT COST | AMOUNT
| SRW-C7 | 0 | 0 | 13 | Exempt | 0
| GUY-DOWN | 0 | 0 | 13 | Exempt | 0
|  | ======= | ======= |  |  | =======
|  | 0 | 0 |  |  | 0
| EXEMPT MATERIAL --- TELCO |  |  | 11.00 HRS | 35.5 | 390.55
| SUPPLY EXPENSE |  |  | 390.55 | 0.05 | 19.53
** | TOTAL MATERIAL |  |  |  |  | 410.08
| PLACING LABOR |  |  | 11.00 HRS | 157.89 | 1736.83
| SPLICING LABOR |  |  | 0.00 HRS | 157.89 | 0
** | TOTAL LABOR |  |  |  |  | 1736.83
| CONTRACT |  |  |  |  | 2062.32
** | TOTAL CONTRACT |  |  |  |  | 2062.32
| ENGINEERING |  |  | 3.92 HRS | 137.92 | 541
** | TOTAL ENGINEERING |  |  |  |  | 541
| TOTAL MATL, LABOR, CONTRACT, ENGR |  |  |  |  | 4750.23
** | GRAND TOTAL |  |  |  |  | 4750.23
| LABOR HOURS: |  |  | 11
| ENGR HOURS: |  |  | 3.92
| OVERHEAD COST: |  |  | 0
Generated: 07/29/2024, 06:48 PM
RQST By: ARAMIS
**** CONSTRUCTION DETAILS ****
Part A
CFAS Project #: A02SMVJ
CMC: ALHMG
FRC: 8645C
Pricing Date: 07/29/2024
| ITEM DESCRIPTION | MCF | FKF | QTY | UNIT COST | AMOUNT
| HANDHOLE10X15 | 0 | 0 | 4 | Exempt | 0
| INNERDUCT-1 | 0 | 0 | 280 | Exempt | 0
|  | ======= | ======= |  |  | =======
|  | 0 | 0 |  |  | 0
** | TOTAL MATERIAL |  |  |  |  | 0
| PLACING LABOR |  |  | 0.00 HRS | 157.89 | 0
| SPLICING LABOR |  |  | 0.00 HRS | 157.89 | 0
** | TOTAL LABOR |  |  |  |  | 0
| CONTRACT |  |  |  |  | 2812.96
** | TOTAL CONTRACT |  |  |  |  | 2812.96
| ENGINEERING |  |  | 1.08 HRS | 137.92 | 148.81
** | TOTAL ENGINEERING |  |  |  |  | 148.81
| TOTAL MATL, LABOR, CONTRACT, ENGR |  |  |  |  | 2961.77
| COST ADJUSTMENT - OTHER |  |  |  |  | 273
** | GRAND TOTAL |  |  |  |  | 3234.77
| LABOR HOURS: |  |  | 0
| ENGR HOURS: |  |  | 1.08
| OVERHEAD COST: |  |  | 0
Generated: 07/29/2024, 06:48 PM
RQST By: ARAMIS
**** CONSTRUCTION DETAILS ****
Part A
CFAS Project #: A02SMVJ
CMC: ALHMG
FRC: 2M
Pricing Date: 07/29/2024
| ITEM DESCRIPTION | MCF | FKF | QTY | UNIT COST | AMOUNT
| TRAN-REGULAR | 0 | 0 | 2 | Exempt | 0
|  | ======= | ======= |  |  | =======
|  | 0 | 0 |  |  | 0
| EXEMPT MATERIAL --- TELCO |  |  | 4.86 HRS | 2.33 | 11.32
| SUPPLY EXPENSE |  |  | 11.32 | 0.05 | 0.57
** | TOTAL MATERIAL |  |  |  |  | 11.89
| PLACING LABOR |  |  | 4.86 HRS | 110 | 534.09
| SPLICING LABOR |  |  | 0.00 HRS | 110 | 0
** | TOTAL LABOR |  |  |  |  | 534.09
| CONTRACT |  |  |  |  | 0
** | TOTAL CONTRACT |  |  |  |  | 0
| ENGINEERING |  |  | 0.36 HRS | 135.13 | 48.82
** | TOTAL ENGINEERING |  |  |  |  | 48.82
| TOTAL MATL, LABOR, CONTRACT, ENGR |  |  |  |  | 594.8
** | GRAND TOTAL |  |  |  |  | 594.8
| LABOR HOURS: |  |  | 4.86
| ENGR HOURS: |  |  | 0.36
| OVERHEAD COST: |  |  | 0
Generated: 07/29/2024, 06:48 PM
RQST By: ARAMIS
**** RETIREMENT DETAILS ****
Part B
CFAS Project #: A02SMVJ
CMC: ALHMG
FRC: 1X
Pricing Date: 07/29/2024
YR | ITEM DESCRIPTION | QTY | RETIREMENT |  | COST REMVL
|  |  | $/UNIT | AMT | $/UNIT | AMT
1900 | SRW-C7 | 2 | 0 | 0 | 0 | 0
1900 | GUY-DOWN | 2 | 0 | 0 | 223.3 | 446.6
|  |  |  | ======= |  | =======
|  |  |  | 0 |  | 446.6
** | TOTAL LABOR |  |  |  |  | 446.6
| CONTRACT |  |  |  |  | 386.56
** | TOTAL CONTRACT |  |  |  |  | 386.56
=======
| ENGINEERING | 1.93 HRS |  |  | 135.13 | 260.7
=======
** | TOTAL ENGINEERING |  |  |  |  | 260.7
| TOTAL MATL, LABOR, CONTRACT, ENGR |  |  |  |  | 1093.86
| EXEMPT MATERIAL - TELCO |  |  | 4.06 HRS | 0 | 0
|  |  |  | ======= |  | =======
** | GRAND TOTAL |  |  | 0 |  | 1093.86
| LABOR HOURS: | 4.06
| ENGR HOURS: | 1.93
| OVERHEAD COST: | 0
Generated: 07/29/2024, 06:48 PM
RQST By: ARAMIS
**** DETAILED PRICING SUMMARY ****
Part C
CFAS Project #: A02SMVJ
CMC: ALHMG
Pricing Date: 07/29/2024
PLANT TYPE | GROSS ADDS | PLANT RETIRED | COST OF REMOVAL | MAINTENANCE
C | 452592.52 | 0 | 0 | 0
X | 0 | 0 | 1093.86 | 0
M | 0 | 0 | 0 | 594.8
| ======= | ======= | ======= | =======
| 452592.52 | 0 | 1093.86 | 594.8
TOTAL MCF |  | 0
TOTAL FKF |  | 7416.628
TOTAL CONTRACT |  | 56945.29
TOTAL ENGINEERING |  | 22907.2
GROSS EXPENDITURES |  | 453686.38
NET ADDITIONS |  | 453686.38
| TOTAL LABOR HOURS: | 1089.38
| TOTAL ENGR HOURS: | 166.13
| TOTAL M DOLLARS: | 594.8
| TOTAL OVERHEAD DOLLARS: | 0
Generated: 07/29/2024, 06:48 PM
RQST By: ARAMIS
**** MCF/FKF DETAIL SUMMARY ****
Part D
CFAS Project #: A02SMVJ
CMC: ALHMG
Pricing Date: 07/29/2024
CABLE TYPE | #PRS | QTY | PIC | PULP
CONT-PL-CABLE | 0 | 385 | 0 | 0
|  | ======= | ======= | =======
TOTAL |  | 385 | 0 | 0
FIBER TYPE | #FBRS | QTY | FKF
EVOLV8/10OTIP | 8 | 19 | 0.152
FIBER-TELCO | 0 | 3149 | 0
5BQ2MR-432 | 432 | 563 | 234.576
FNAP-CBL-024 | 24 | 12506 | 296.784
FNAP-CBL-216EUC | 216 | 6369 | 1358.424
FNAP-CBL-144 | 144 | 7897 | 1125.648
5B92MT-072 | 72 | 1662 | 118.224
FNAP-CBL-048 | 48 | 9443 | 449.424
FNAP-CBL-072 | 72 | 4738 | 338.256
FNAP-CBL-432EUC | 432 | 7813 | 3349.296
5BQ2MT-144 | 144 | 110 | 14.4
FNAP-CBL-024EUC | 24 | 2019 | 47.736
FNAP-CBL-048EUC | 48 | 1755 | 83.28
|  | ======= | =======
TOTAL |  | 58043 | 7416.2
Generated: 07/29/2024, 06:48 PM
RQST By: ARAMIS
**** DETAILED PRICING ERROR LISTING ****
Part E
CFAS Project #: A02SMVJ
CMC: ALHMG
Pricing Date: 07/29/2024
THE FOLLOWING ERROR MESSAGE(S) APPLY TO FRC: errorMessage
NO ERRORS OR WARNINGS WERE GENERATED IN PRODUCING THIS REPORT
Generated: 07/29/2024, 06:48 PM
RQST By: ARAMIS
**** BILLING SUMMARY ****
Part F
CFAS Project #: A02SMVJ
CMC: ALHMG
Billing?: Y
Pricing Date: 07/29/2024
COST ESTIMATE AS PER REQUEST
(1) ENGINEERING COST |  | 1.68
845C | 1.68
822C | 0
1C | 0
1X | 0
8645C | 0
2M | 0
(2) PLANT LABOR COST |  | 0
845C | 0
822C | 0
1C | 0
1X | 0
8645C | 0
2M | 0
(3) MATERIAL COST |  | 0
845C | 0
822C | 0
1C | 0
1X | 0
8645C | 0
2M | 0
(4) CONTRACT COST |  | 0
845C | 0
822C | 0
1C | 0
1X | 0
8645C | 0
2M | 0
COST ADJUSTMENT - CONT |  | 20
845C | 20
822C | 0
1C | 0
1X | 0
8645C | 0
2M | 0
(5) OVERHEAD COST |  | 0
845C | 0
822C | 0
1C | 0
1X | 0
8645C | 0
2M | 0
COST ADJUSTMENT - OTHER |  | 93137
845C | 13443
822C | 79421
1C | 0
1X | 0
8645C | 273
2M | 0
=======
Subtotal Cost |  | 93158.68
DISTRIBUTIONS OF COLLECTIONS
Total Cost minus Salvage | 93158.68
Generated: 07/29/2024, 06:48 PM
RQST By: ARAMIS
**** LABOR RATE SUMMARY ****
Part L
CFAS Project #: A02SMVJ
CMC: ALHMG
Pricing Date: 07/29/2024
PAC CLASS | LABOR CLASS | CREW ID | RESOURCE DESCRIPTION | HOURS | LOADED LABOR RATE/HOUR | TOTAL
C | AP/S | ALHMGT1 | STUDDARD / TELCO | 772.52 | 157.89 | 121973.18
M | AP/S | ALHMGT1 | STUDDARD / TELCO | 4.86 | 110 | 534.6
C | AP | ALHMGT1 | STUDDARD / TELCO | 133.7 | 157.89 | 21109.89
C | AS | ALHMGT1 | STUDDARD / TELCO | 174.02 | 157.89 | 27476.02
C | ED | ALHMGT1 | STUDDARD / TELCO | 0 | 157.89 | 0
X | AR | ALHMGT1 | STUDDARD / TELCO | 4.06 | 110 | 446.6
|  |  |  | ======= |  | =======
|  |  |  | 1089.16 |  | 171575.27
C | AP | ALDDCT1 | PENNINGTON / TELCO | 109.25 | 144.89 | 15829.23
C | ED | ALDDCT1 | PENNINGTON / TELCO | 0 | 144.89 | 0
|  |  |  | ======= |  | =======
|  |  |  | 381.3 |  | 55283.08